## Sheet1
Backlog ID | User Story / Requirement | Owner | Priority | Sprint
PB-01 | Gather HR and payroll system requirements | PO | High | Sprint-1
PB-02 | Prepare Software Requirement Specification (SRS) | PO | High | Sprint-1
PB-03 | Design system architecture | PO | High | Sprint-1
PB-04 | Setup GitHub repository and branch protection | DevOps | High | Sprint-1
PB-05 | Learn Jenkins, Docker, and CI/CD concepts (Preparation) | DevOps | Medium | Sprint-1
PB-06 | Create database schema (users table with role column) | DBE | High | Sprint-1
PB-07 | As a user, I want to login with email and password | FE + BE | High | Sprint-1
PB-08 | As a user, I want to see role-based dashboard after login (Admin/HR/Employee) with sidebar navigation | FE | High | Sprint-1
PB-09 | Test login and role-based dashboard functionality | QA | High | Sprint-1
PB-10 | Conduct daily standups and remove blockers | SM | High | Sprint-1
PB-11 | Facilitate Sprint Planning, Review, and Retrospective | SM | High | Sprint-1
PB-12 | As a user, I want to reset password via email OTP | BE | High | Sprint-2
PB-13 | Implement Role-Based Access Control (RBAC) for sidebar menus | BE | High | Sprint-2
PB-14 | As a user, I want to see charts on dashboard (employee count by department, leave status) | FE + BE | High | Sprint-2
PB-15 | Test forgot password | QA | High | Sprint-2
PB-16 | Write clear stories for employees list, add, edit with what fields needed and validation rules | PO | High | Sprint-3
PB-17 | As HR/Admin, I want to view all employees in a list with search | FE + BE | High | Sprint-3
PB-18 | As HR/Admin, I want to add new employees (creates login account + employee profile) | FE + BE | High | Sprint-3
PB-19 | As HR/Admin, I want to edit existing employee details | FE + BE | High | Sprint-3
PB-20 | Test Employee CRUD operations and permissions | QA | High | Sprint-3
PB-21 | As an employee, I want to apply for leave with type, dates, and reason | FE + BE | High | Sprint-4
PB-22 | As an employee, I want to view my leave balance and history | FE | High | Sprint-4
PB-23 | As HR/Admin, I want to see all pending leave applications | FE + BE | High | Sprint-4
PB-24 | As HR/Admin, I want to approve/reject leave requests with comments | FE + BE | High | Sprint-4
PB-25 | As an employee, I want email notification on leave approval/rejection | BE | Medium | Sprint-4
PB-26 | Test leave application, approval, and email notifications | QA | High | Sprint-4
PB-27 | As HR/Admin, I want to run monthly payroll for all employees | BE | High | Sprint-5
PB-28 | As an employee, I want to view and download payslip as PDF | FE + BE | High | Sprint-5
PB-29 | As HR/Admin, I want to view payroll history and summary | FE | Medium | Sprint-5
PB-30 | Test payroll run, payslip generation, and PDF download | QA | High | Sprint-5
PB-31 | Containerize application using Docker | DevOps | High | Sprint-6
PB-32 | Create automated build and deployment pipeline (CI/CD) using Jenkins | DevOps | High | Sprint-6
PB-33 | Deploy complete application on cloud platform | DevOps | High | Sprint-6
PB-34 | As a user, I want to see summary stats on reports page (total employees, leaves, payroll) | FE + BE | High | Sprint-7
PB-35 | As a user, I want to see employee growth chart (line chart - last 6 months) | FE + BE | High | Sprint-7
PB-36 | Final production deployment and system handover | All | High | Sprint-6
PB-37 | Create user manual and technical documentation | PO | Medium | Sprint-7